## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | G. Ganesh Sai Ram | 2026-10-10 | Streamlit frontend has a very basic two-column layout without custom styling, status badges, or clean spacing. | Sprint 1 | G. Ganesh Sai Ram | User Interface | Upgraded ui/app.py with 5-tier Severity Pyramid metrics, 4 Complexity cards, Quality Assessment scores, and 5 report tabs. | 2026-10-26 | Closed | Resolved in Sprint 2; dashboard now renders all 6 security report fields and quality metrics.
2 | G. Ganesh Sai Ram | 2026-10-11 | Frontend directly imports Python functions instead of communicating through a decoupled FastAPI backend. | Sprint 1 | G. Ganesh Sai Ram | Logical | Built FastAPI backend (services/api.py) with /api/v1/analyze and /api/v1/history endpoints plus SQLite persistence | 2026-10-26 | Closed | Resolved in Sprint 2; Streamlit now communicates with FastAPI on port 8000.
3 | G. Ganesh Sai Ram | 2026-10-13 | Automated unit test scripts inside the tests/ folder have not been written yet for the parser and RAG modules. | Sprint 1 | G. Ganesh Sai Ram | Standards | Added tests/test_agents.py to automatically validate parallel agent accuracy on Python and Java sample files. | 2026-10-28 | Closed | Resolved in Sprint 2; automated validation suite passes for both Python and Java samples.
4 | G. Ganesh Sai Ram | 2026-10-24 | Parallel agents caused a 120s ReadTimeoutError because rag/retriever.py re-computed embeddings on CPU via FAISS.from_documents() on every call. | Sprint 2 | G. Ganesh Sai Ram | Logical | Cached the HuggingFaceEmbeddings instance in rag/embeddings.py and switched rag/retriever.py to FAISS.from_embeddings() using stored ChromaDB vectors. | 2026-10-27 | Closed | Retrieval latency reduced from >120s to <0.05s during parallel LangGraph execution.
5 | G. Ganesh Sai Ram | 2026-10-26 | Uvicorn reloader threw sqlite3.OperationalError: unable to open database file on Windows when initializing data/reviews.db | Sprint 2 | G. Ganesh Sai Ram | Maintainability | Anchored DB_PATH in services/database.py to the absolute project root (ROOT_DIR / "data" / "reviews.db") and auto-created the data/ folder. | 2026-10-27 | Closed | SQLite database initializes and saves review history reliably across Uvicorn workers.
6 | G. Ganesh Sai Ram | 2026-10-27 | Streamlit file watcher raised ModuleNotFoundError: No module named 'torchvision' when inspecting transformers modules. | Sprint 2 | G. Ganesh Sai Ram | Maintainability | Created .streamlit/config.toml (fileWatcherType = "none") and moved fallback src.workflow import inside the execution block in ui/app.py. | 2026-10-27 | Closed | Eliminated watcher tracebacks and improved Streamlit startup speed.
7 | G. Ganesh Sai Ram | 2026-10-28 | Interactive RAG Conversational Code Assistant, PR Summary Agent, and downloadable report export buttons are not yet integrated into the UI. | Sprint 2 | G. Ganesh Sai Ram | User Interface | Scoped out of Milestone 2 per project roadmap; scheduled for implementation in Milestone 3 (Sprint 3). | 2026-10-29 | Open | Tracked for Sprint 3 (Milestone 3) delivery.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others